## 1. Product Overview
Item | Description
Product Name | Compliance Helper for MSME GST & E-Invoicing
Product Vision/ Purpose | To simplify GST compliance for MSMEs by automating invoice processing, reconciliation, and error detection — reducing dependency on auditors and minimising penalties.
Business Goals / Key Success factors | 1. Automate invoice processing (OCR + ML) to eliminate manual data entry. 2. Detect mismatches and missing data proactively to avoid GST penalties. 3. Reduce compliance costs for small businesses. 4. Achieve high user adoption among MSMEs with limited GST knowledge.
Primary Stakeholders | MSME business owners, accountants/auditors Chandrashekhar S Hadimani, Athmi S Rai – Customer Contact)

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up with email and OTP so that I can access my account securely. | Registration screen, OTP Generation & Validation, Login screen, Pop-up on success/failure, Login Error Screen | Must Have |  | In Progress | Chetan K (Dev Lead)/Chethan Kumar HM/Looga Paramesh | Valid registration, OTP expiryInvalid login | Chethan Kumar H M/ Chetan K/Logaa Paramesh
Pop Ups once registered
Login screen
OTP Generation
Sending OTP
Login Error Screen
US2
|  | US7 |  | Dashboard UI with charts/graphs, Analytics API integration, Trends & summary widgets
E2 | Dashboard | US5 | As a user, I want to view analytics on a dashboard so that I can see trends quickly. |  | Should Have |  | In Progress | Harshitha M Raj / Gaddaley Vyshnavi Rao | Dashboard loads in <3s,Data accuracy check | Chethan Kumar H M/Chetan K
|  | US6 |  |  | Could Have
US3
E3 | Invoice Upload & OCR | US3 | As an MSME owner, I want to upload scanned invoices (PDF/image) so the system extracts data automatically. | OCR engine integration (Tesseract/Cloud Vision), PDF/image parser, data extraction pipeline | Must Have |  | To Do | Chetan K / Gaddaley Vyshnavi Rao/Chethan Kumar H M | PDF upload success, OCR accuracy >90,Unsupported format error | Chethan Kumar H M/ Chetan K / Logaa Paramesh
E4 | GST Reconciliation | US4 | As an MSME owner, I want purchase and sales records matched automatically so I can spot mismatches early. | GSTR-2A vs purchase register matching logic, mismatch report generation, alert system | Must Have |  | To Do | Chetan K/Chethan Kumar H M /Chandrashekar | Correct match identified, Mismatch flagged, Alert notification sent | Chethan Kumar H M/Chetan k/Athmi S Rai
E5 | Compliance Check & Error Detection | US5b | As an MSME owner, I want the system to flag missing or incorrect GST fields so I can fix them before filing. | Rule-based validation engine, missing field detector, penalty risk estimator | Must Have |  | To Do | Harshitha M Raj/Logaa Paramesh/Athmi S Rai | Missing GSTIN flagged, Incorrect tax rate detected, Penalty risk shown | Vyshnavi/Harshitha/Chetan Kumar H M /Chetan K
E6 | Reporting & Export | US6 | As an MSME owner, I want to export GST summary reports in PDF/Excel so I can share them with my auditor. | Report generation module, PDF/Excel export, email share option | Should Have |  | Planned | Gaddaley Vyshnavi Rao | Report generated correctly, Export downloads without error | Chethan Kumar H M/Chandrashekar
E7 | Notifications & Alerts | US7 | As a user, I want email/in-app alerts for due dates and mismatches so I never miss a GST deadline. | Notification service, due-date calendar, alert rules engine | Should Have |  | To Do | Chandrashekhar S Hadimani / Athmi S Rai | Due date alert sent 3 days prior, Mismatch alert triggered | Chethan Kumar H M/Chetan K

## 3. Roadmap
Release / Timeline | Focus Area | Key Features | Dependencies | Demo Status
Week 1–2 | Market research on MSME GST pain points; customer interviews; competitor analysis; define product scope | Problem Validation & Research | • Access to MSME business owners / auditors for interviews • GST portal documentation (GSTN official docs) • Survey tools (Google Forms / Typeform) • GitHub repo initialized (https://github.com/chetank23/GST-INVOICE-AI.git) • Team onboarding & role alignment | On Track
Week 3–4 | Integrate OCR engine to extract data from scanned invoices (PDF/images); validate extraction accuracy | OCR & Invoice Parsing Prototype | • OCR library: Tesseract OCR or Google Cloud Vision API (API key required) • PDF parsing library: PyMuPDF / pdfplumber • Sample invoice dataset (PDF, JPG, PNG formats) • Python environment with dependencies: pytesseract, Pillow, pdfplumber • Cloud storage (AWS S3 / Firebase) for uploaded invoices • Week 1–2 research outputs (invoice field definitions) | Planned
Week 5–6 | Build rule-based GST compliance validator; implement billing/invoice generation module; mismatch detection logic | GST Rule Engine + Billing System | • GSTN API access or GST rule documentation (CGST/IGST/SGST rate tables) • Week 3–4 OCR output as structured JSON input • Database setup (PostgreSQL / Firebase Firestore) for storing invoice records • Backend framework (Flask / FastAPI) with REST API endpoints • GST rate master data (HSN/SAC code list) • Payment gateway SDK (Razorpay / Stripe) for billing module • Authentication system (JWT tokens) — from Week 1–2 auth setup | Planned
Week 7–8 | Integrate WhatsApp API for invoice sharing & alerts; build analytics dashboard; end-to-end testing & QA | WhatsApp Billing Integration + Dashboard + Testing | • WhatsApp Business API (Meta Developer account + approved business number) • Twilio or 360dialog as WhatsApp messaging provider • Week 5–6 GST rule engine & billing APIs (must be stable) • Frontend framework (React.js / Flutter) for dashboard • Charting library (Chart.js / Recharts) for analytics widgets • End-to-end test suite (Pytest / Selenium) setup • CI/CD pipeline (GitHub Actions) for automated testing • UAT with at least 2–3 MSME customer contacts • Deployment environment (AWS EC2 / Heroku / Railway) | Planned

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Next time what will you do differently
Used GitHub for version control — automatic versioning helped track changes | Sprint planning was not detailed enough for IA1 deadline | Define sprint goals clearly at start of each release | Team Lead – Logaa Paramesh
Regular team sync meetings kept everyone aligned | No automated tests in place — all testing manual | Set up automated test pipeline in next sprint | Test Lead – Chethan Kumar H M
GitHub URL documented for easy access to PoC | Customer persona research started late | Begin customer interviews in parallel with development | Customer Contact – Athmi S Rai